Development of Social Determinants of Health country profiles and

dashboard for countries in South-East Asia

Terms of Reference

Complete below or leave the following wording: See attached document.

1. Purpose of the APW

This APW is to produce country social determinants of health profile and dashboard from existing official data and information. Trends of socio-economic and cultural changes relevant to health equity would be presented with visualized data (infographics or dynamic visual data presentation) and easy to download/print correlation between health determinants (across SDGs) and health outcomes (SDG3). Where it is possible, AI can be applied to summarize/interpret the data with credible data sources.

2. Background

WHO South-East Asia countries committed to support Member States to address social determinants of health and develop coherence policy actions to address social determinants of health, health inequities, and gaps to achieve universal health coverage ensuring no one is leaving behind. Having ready information and data analysis to support development of health policy, plans, and programmes with key determinants effecting health conditions, health behaviors, and people’s ability to utilize health systems are important to successful universal health coverage. Key determinants of health will demonstrate underlying causes of the causes of ill health which beyond individual controls.

Policy of other sectors can benefit as well as affected people’s health outcomes due to changes in enabling conditions such as housing policies that improve overall environments where people live and spend 2/3 of their time a day. Improper housing can affect mental and physical health especially respiratory infections in children and adults. Indoor

air pollutions and led poison are known to be leading cause of morbidity among people in settlements where there is no ventilation or proper materials in constructing the house. People living under poverty both in urban and rural areas have less opportunities to use health care services due to several factors ranging from distance to unaffordable cost, or distrust in health system.

Social determinants of health are placed in almost all of the SDGs targets. Improvement of other SDGs can improve SDG3 targets as they are highly correlated, e.g. countries that achieve the SDG4 (education) targets, especially female education, is likely to improve maternal and newborn health and reduce maternal mortality rates. Improve employment rates and social protection can improve accessibility to health. Thus, having consolidate data that demonstrate determinants of health in the South-East Asia Region is important for strategic investment and collaborative cross sectoral actions.

WHO South-East Asian countries namely Bangladesh, Bhutan, DPR Korea, India, Maldives, Myanmar, Nepal, Sri Lanka, Thailand and Timor Leste, have different socioeconomic and political systems. Each country deserves to have their own social determinants of health indexes and data set. Trends of rapid changing geopolitical architectures and environmental changes would be critical for each country to consider people capacities and vulnerabilities to be prepared for these significant changes effecting their health and wellbeing.

Therefore, having dashboard that informs each country of specific social determinants of health and the trends in one place along with country current profile will facilitate country to build health systems and responses cohesively to the health needs.

3. Planned timelines (subject to confirmation)

Start date: 01/08/2025 End date: 31/11/2025.

Total duration: 4 months

4. Requirements - Work to be performed.

Objective 1: Collect existing links to data from UN system, national segregated data, WHO observations data, WHO Health Equity Assessment and define key health determinants indicators appropriate to each country of WHO South-East Asia region.

Output 1.1: Set of indicators and links to data for each country health profiles and its determinants (update from WHO-SEARO existing data set and additional data as needed.)

Output 1.2: Draft specific social determinants of health profiles for 10 countries in South-East Asia with visualized data

Objective 2: Develop trends and analysis of health determinants and gaps of inequities as per existing information available in each country.

Output 2.1: Use appropriate tool (e.g. health equity analysis tool) to highlight trends of health inequities in countries in South-East Asia

Output 2.2: Highlights key policy changes affecting health outcomes and health inequities in countries of South-East Asia, using existing documentations in the past 5 years.

Objective 3: Design appropriate dashboard for social determinants of health indicators South-East Asia region

Output 3.1. Visualized data (infographics, spidergram, comparable indicators, trends, etc.) presenting health determinants that effect health conditions (positively/negatively)

Output 3.2. Visualized data demonstrated the trends linking other SDGs to SDG3 (health) test and upload on website.

Output 3.3 User guide how to use dashboard and produce needed report.

6. Inputs

WHO existing data from WHO observatory data, WHO-HEAT data set, preliminary indicators and data sources found in each country, country specific reports on policies related to social determinants of health, specific SDGs reports.